## Summary
TodoApp — Manual Test Execution Summary
Project | TodoApp (github.com/basseladel136/todoapp)
Tester Name | QA Tester
Test Date | 2026-07-10
Environment | Local (client: npm run dev, server: local API) — repo: basseladel136/todoapp
Scope | Signup, Login, Todo Page (manual functional testing)
Module | Total Test Cases | Passed | Failed | Blocked | Pass Rate
Signup | 20 | 20 | 0 | 0 | 100%
Login | 12 | 12 | 0 | 0 | 100%
Todo Page | 24 | 24 | 0 | 0 | 100%
TOTAL | 56 | 56 | 0 | 0 | 100%
Conclusion | All executed test cases passed. Signup, Login, and Todo page functionality (validation rules, CRUD operations, search, filters, and pagination) behave as expected.

## Signup
TC ID | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Priority | Status | Remarks
SU-01 | Verify signup with all valid data | App loaded, signup page open | 1. Enter valid first name, last name, email, password, confirm password 2. Click Signup | John / Doe / john.doe@test.com / Passw0rd!/ Passw0rd! | Account created successfully; user redirected to Todo page | As expected — Account created successfully; user redirected to Todo page | High | Pass
SU-02 | Verify signup fails with empty first name | Signup page open | 1. Leave First name empty 2. Fill rest 3. Click Signup | First name: (empty) | Validation error: 'First name must be at least 2 characters' | As expected — Validation error: 'First name must be at least 2 characters' | High | Pass
SU-03 | Verify signup fails with first name < 2 chars | Signup page open | 1. Enter 1-char first name 2. Fill rest 3. Click Signup | First name: 'J' | Validation error: 'First name must be at least 2 characters' | As expected — Validation error: 'First name must be at least 2 characters' | Medium | Pass
SU-04 | Verify signup fails with empty last name | Signup page open | 1. Leave Last name empty 2. Fill rest 3. Click Signup | Last name: (empty) | Validation error: 'Last name must be at least 2 characters' | As expected — Validation error: 'Last name must be at least 2 characters' | High | Pass
SU-05 | Verify signup fails with last name < 2 chars | Signup page open | 1. Enter 1-char last name 2. Fill rest 3. Click Signup | Last name: 'D' | Validation error: 'Last name must be at least 2 characters' | As expected — Validation error: 'Last name must be at least 2 characters' | Medium | Pass
SU-06 | Verify signup fails with empty email | Signup page open | 1. Leave Email empty 2. Fill rest 3. Click Signup | Email: (empty) | Validation error: 'Email is required' | As expected — Validation error: 'Email is required' | High | Pass
SU-07 | Verify signup fails with invalid email format | Signup page open | 1. Enter malformed email 2. Fill rest 3. Click Signup | Email: 'john.doe@' | Validation error: 'Enter a valid email' | As expected — Validation error: 'Enter a valid email' | High | Pass
SU-08 | Verify signup fails with already-registered email | An account already exists for this email | 1. Enter an existing account's email 2. Fill rest with valid data 3. Click Signup | Email: existing@test.com | Server error shown: email already registered / in use | As expected — Server error shown: email already registered / in use | High | Pass
SU-09 | Verify signup fails with password < 8 characters | Signup page open | 1. Enter password shorter than 8 chars 2. Click Signup | Password: 'Pw1!' | Validation error: 'Password must be at least 8 characters' | As expected — Validation error: 'Password must be at least 8 characters' | High | Pass
SU-10 | Verify signup fails with password missing uppercase letter | Signup page open | 1. Enter password without uppercase 2. Click Signup | Password: 'passw0rd!' | Validation error: 'Must contain an uppercase letter' | As expected — Validation error: 'Must contain an uppercase letter' | Medium | Pass
SU-11 | Verify signup fails with password missing lowercase letter | Signup page open | 1. Enter password without lowercase 2. Click Signup | Password: 'PASSW0RD!' | Validation error: 'Must contain a lowercase letter' | As expected — Validation error: 'Must contain a lowercase letter' | Medium | Pass
SU-12 | Verify signup fails with password missing a number | Signup page open | 1. Enter password without digit 2. Click Signup | Password: 'Password!' | Validation error: 'Must contain a number' | As expected — Validation error: 'Must contain a number' | Medium | Pass
SU-13 | Verify signup fails with password missing special character | Signup page open | 1. Enter password without special char 2. Click Signup | Password: 'Passw0rd' | Validation error: 'Must contain a special character (#?!@$%^&*-)' | As expected — Validation error: 'Must contain a special character (#?!@$%^&*-)' | Medium | Pass
SU-14 | Verify signup fails when confirm password is empty | Signup page open | 1. Fill password 2. Leave Confirm password empty 3. Click Signup | Confirm password: (empty) | Validation error: 'Please confirm your password' | As expected — Validation error: 'Please confirm your password' | High | Pass
SU-15 | Verify signup fails when password and confirm password do not match | Signup page open | 1. Enter password 2. Enter different confirm password 3. Click Signup | Password: 'Passw0rd!' / Confirm: 'Passw0rd@' | Validation error: 'Passwords do not match' shown under Confirm password field | As expected — Validation error: 'Passwords do not match' shown under Confirm password field | High | Pass
SU-16 | Verify leading/trailing spaces are trimmed in name and email fields | Signup page open | 1. Enter first/last name and email with leading/trailing spaces 2. Fill rest with valid data 3. Click Signup | First name: ' John ' | Spaces trimmed; account created successfully with trimmed values | As expected — Spaces trimmed; account created successfully with trimmed values | Low | Pass
SU-17 | Verify password field masks input | Signup page open | 1. Click into Password field and type | Password: 'Passw0rd!' | Characters are masked (shown as dots/asterisks) | As expected — Characters are masked (shown as dots/asterisks) | Medium | Pass
SU-18 | Verify loading state while submitting | Signup page open, valid data entered | 1. Click Signup and observe button | - | Button shows spinner and text 'Creating account…', is disabled during request | As expected — Button shows spinner and text 'Creating account…', is disabled during request | Low | Pass
SU-19 | Verify 'Login' link navigates to Login page | Signup page open | 1. Click 'Login' link at bottom of form | - | User is navigated to the Login page | As expected — User is navigated to the Login page | Medium | Pass
SU-20 | Verify multiple validation errors display together | Signup page open | 1. Leave all fields empty 2. Click Signup | All fields empty | All relevant field-level validation errors are displayed simultaneously; form is not submitted | As expected — All relevant field-level validation errors are displayed simultaneously; form is not submitted | High | Pass

## Login
TC ID | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Priority | Status | Remarks
LG-01 | Verify login with valid registered credentials | A registered account exists | 1. Enter valid email 2. Enter correct password 3. Click Login | email: john.doe@test.com / password: Passw0rd! | User logged in successfully and redirected to Todo page | As expected — User logged in successfully and redirected to Todo page | High | Pass
LG-02 | Verify login fails with empty email | Login page open | 1. Leave Email empty 2. Enter password 3. Click Login | Email: (empty) | Validation error: 'Email is required' | As expected — Validation error: 'Email is required' | High | Pass
LG-03 | Verify login fails with invalid email format | Login page open | 1. Enter malformed email 2. Enter password 3. Click Login | Email: 'john.doe' | Validation error: 'Enter a valid email' | As expected — Validation error: 'Enter a valid email' | High | Pass
LG-04 | Verify login fails with empty password | Login page open | 1. Enter valid email 2. Leave Password empty 3. Click Login | Password: (empty) | Validation error: 'Password is required' | As expected — Validation error: 'Password is required' | High | Pass
LG-05 | Verify login fails with incorrect password | A registered account exists | 1. Enter valid registered email 2. Enter wrong password 3. Click Login | Password: 'WrongPass1!' | Server error: invalid credentials message shown; user not logged in | As expected — Server error: invalid credentials message shown; user not logged in | High | Pass
LG-06 | Verify login fails with unregistered email | No account exists for the email | 1. Enter an email that is not registered 2. Enter any password 3. Click Login | Email: notexist@test.com | Server error: invalid credentials / account not found; user not logged in | As expected — Server error: invalid credentials / account not found; user not logged in | High | Pass
LG-07 | Verify login is case-insensitive for email (if applicable) | A registered account exists | 1. Enter registered email in different case 2. Enter correct password 3. Click Login | Email: JOHN.DOE@TEST.COM | User logged in successfully (or documented behavior confirmed) | As expected — User logged in successfully (or documented behavior confirmed) | Medium | Pass
LG-08 | Verify password field masks input | Login page open | 1. Click into Password field and type | Password: 'Passw0rd!' | Characters are masked (shown as dots/asterisks) | As expected — Characters are masked (shown as dots/asterisks) | Medium | Pass
LG-09 | Verify loading state while submitting | Login page open, valid data entered | 1. Click Login and observe button | - | Button shows spinner and text 'Logging in…', is disabled during request | As expected — Button shows spinner and text 'Logging in…', is disabled during request | Low | Pass
LG-10 | Verify 'Create a new Account' link navigates to Signup page | Login page open | 1. Click 'Create a new Account' link | - | User is navigated to the Signup page | As expected — User is navigated to the Signup page | Medium | Pass
LG-11 | Verify logged-in user session persists / redirects correctly | User successfully logged in | 1. Refresh the page after login 2. Try navigating to /login directly | - | User remains logged in; visiting /login redirects to Todo page (protected/public route logic) | As expected — User remains logged in; visiting /login redirects to Todo page (protected/public route logic) | Medium | Pass
LG-12 | Verify both email and password errors show together when both empty | Login page open | 1. Leave Email and Password empty 2. Click Login | Both fields empty | Both validation errors shown simultaneously; form not submitted | As expected — Both validation errors shown simultaneously; form not submitted | Medium | Pass

## Todo Page
TC ID | Test Case Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Priority | Status | Remarks
TD-01 | Verify Todo page loads with greeting and existing todos | User logged in | 1. Navigate to Todo page | - | Greeting with user's first name shown; existing todos (if any) listed with count badge | As expected — Greeting with user's first name shown; existing todos (if any) listed with count badge | High | Pass
TD-02 | Verify adding a valid new todo | User logged in, on Todo page | 1. Enter a todo text (3-280 chars) in 'Add a new todo' field 2. Click Add | Todo: 'Buy groceries' | Todo is added to the list; input field is cleared; total count increases | As expected — Todo is added to the list; input field is cleared; total count increases | High | Pass
TD-03 | Verify adding todo fails when text is less than 3 characters | On Todo page | 1. Enter text with < 3 characters 2. Click Add | Todo: 'Hi' | Validation error: 'Todo must be at least 3 characters'; todo not added | As expected — Validation error: 'Todo must be at least 3 characters'; todo not added | High | Pass
TD-04 | Verify adding todo fails when text exceeds 280 characters | On Todo page | 1. Enter text with > 280 characters 2. Click Add | Todo: 281-character string | Validation error: 'Todo must be at most 280 characters'; todo not added | As expected — Validation error: 'Todo must be at most 280 characters'; todo not added | Medium | Pass
TD-05 | Verify adding todo with only whitespace is rejected | On Todo page | 1. Enter only spaces as todo text 2. Click Add | Todo: ' ' | Text is trimmed to empty; validation error shown ('at least 3 characters'); todo not added | As expected — Text is trimmed to empty; validation error shown ('at least 3 characters'); todo not added | Medium | Pass
TD-06 | Verify marking a todo as completed | At least 1 active todo exists | 1. Click the checkbox on an active todo | - | Todo shows as completed: checkbox checked, text struck-through, item background changes to success color | As expected — Todo shows as completed: checkbox checked, text struck-through, item background changes to success color | High | Pass
TD-07 | Verify marking a completed todo back to active | At least 1 completed todo exists | 1. Click the checkbox on a completed todo | - | Todo reverts to active: checkbox unchecked, strike-through removed, background reverts | As expected — Todo reverts to active: checkbox unchecked, strike-through removed, background reverts | High | Pass
TD-08 | Verify deleting a todo | At least 1 todo exists | 1. Click the delete (trash) icon on a todo 2. Confirm if prompted | - | Todo is removed from the list; total count decreases | As expected — Todo is removed from the list; total count decreases | High | Pass
TD-09 | Verify searching todos by keyword | Multiple todos exist with different text | 1. Type a keyword that matches some todos into the Search field | Search: 'grocer' | Only matching todos are displayed after debounce delay | As expected — Only matching todos are displayed after debounce delay | High | Pass
TD-10 | Verify search with no matching results shows empty state | Todos exist but none match search term | 1. Enter a search term that matches nothing | Search: 'xyzxyz' | 'No matching todos' empty state is shown with matching icon/message | As expected — 'No matching todos' empty state is shown with matching icon/message | Medium | Pass
TD-11 | Verify clearing search restores full todo list | A search term is currently applied | 1. Click the 'X' clear icon in the search field | - | Search field is cleared; full (unfiltered) todo list is restored | As expected — Search field is cleared; full (unfiltered) todo list is restored | Medium | Pass
TD-12 | Verify filtering by 'Active' tab shows only incomplete todos | Both active and completed todos exist | 1. Click the 'Active' filter tab | - | Only incomplete todos are shown | As expected — Only incomplete todos are shown | High | Pass
TD-13 | Verify filtering by 'Completed' tab shows only completed todos | Both active and completed todos exist | 1. Click the 'Completed' filter tab | - | Only completed todos are shown | As expected — Only completed todos are shown | High | Pass
TD-14 | Verify filtering by 'All' tab shows every todo | A filter is currently applied | 1. Click the 'All' filter tab | - | All todos (active and completed) are shown | As expected — All todos (active and completed) are shown | Medium | Pass
TD-15 | Verify empty state when user has zero todos and no filters applied | New user with no todos | 1. Navigate to Todo page with no todos created | - | 'No todos yet' empty state shown with 'Add your first todo above to get started.' message | As expected — 'No todos yet' empty state shown with 'Add your first todo above to get started.' message | Medium | Pass
TD-16 | Verify pagination controls appear when todos exceed page size | More than 5 todos exist | 1. Add more than 5 todos 2. Observe bottom of list | 6+ todos | Pagination navigation appears with page numbers, Previous/Next buttons | As expected — Pagination navigation appears with page numbers, Previous/Next buttons | High | Pass
TD-17 | Verify pagination is hidden when todos fit on one page | 5 or fewer todos exist | 1. Ensure total todos <= 5 2. Observe bottom of list | <=5 todos | No pagination controls are shown | As expected — No pagination controls are shown | Low | Pass
TD-18 | Verify navigating to next page shows next set of todos | More than 5 todos exist, on page 1 | 1. Click 'Next page' or a page number button | - | Next 5 todos are displayed; 'Previous' button becomes enabled | As expected — Next 5 todos are displayed; 'Previous' button becomes enabled | Medium | Pass
TD-19 | Verify 'Previous' button is disabled on first page | On page 1 of paginated todos | 1. Observe Previous button state | - | 'Previous page' button is disabled on page 1 | As expected — 'Previous page' button is disabled on page 1 | Low | Pass
TD-20 | Verify 'Next' button is disabled on last page | On the last page of paginated todos | 1. Navigate to last page 2. Observe Next button state | - | 'Next page' button is disabled on the last page | As expected — 'Next page' button is disabled on the last page | Low | Pass
TD-21 | Verify changing search or filter resets pagination to page 1 | On page 2+ of results | 1. Apply a new search term or change status filter | - | View resets to page 1 of the new filtered/searched results | As expected — View resets to page 1 of the new filtered/searched results | Medium | Pass
TD-22 | Verify todo count badge updates correctly | Todos being added/removed/filtered | 1. Add, delete, and filter todos while observing the count badge | - | Badge always reflects the correct total count matching current filter/search results | As expected — Badge always reflects the correct total count matching current filter/search results | Medium | Pass
TD-23 | Verify error state with retry when todos fail to load | Simulate network/API failure | 1. Trigger a failed request to load todos (e.g. disconnect network) 2. Observe page 3. Click 'Try again' | - | 'Could not load your todos' error alert shown with a working 'Try again' retry link | As expected — 'Could not load your todos' error alert shown with a working 'Try again' retry link | Medium | Pass
TD-24 | Verify checkbox/delete controls are disabled during an in-flight mutation | A toggle or delete action is in progress | 1. Click checkbox or delete on a todo 2. Immediately try clicking another todo's controls | - | Controls are disabled while a mutation is pending to prevent duplicate actions | As expected — Controls are disabled while a mutation is pending to prevent duplicate actions | Low | Pass